## Budget - Itemized
Phase | Category | Item | Budgeted Cost ($) | Actual Cost ($) | Variance ($)
Phase 1 | Core Construction | 3 Dome Clusters (21 units, Stage B Full) | 600000
Phase 1 | Utilities | Power/Water/Sanitation Infrastructure | 100000
Phase 1 | Utilities | Primary Solar Power System (Off-grid) | 85000
Phase 1 | Staff Housing | Murano Dome Staff Quarters (housing for 4–8) | 175000
Phase 2 | Greenhouse & Grotto | Central Greenhouse + Grotto Pool | 250000
Phase 2 | Aquafarming | Aquafarming Systems Setup | 120000
Phase 3 | Grand Opening | Final Preparations & Event Setup | 30000

## Actuals vs Budget
Phase | Category | Item | Budgeted Cost ($) | Actual Cost ($) | Variance (%)
Phase 1 | Core Construction | 3 Dome Clusters (21 units, Stage B Full) | 600000
Phase 1 | Utilities | Power/Water/Sanitation Infrastructure | 100000
Phase 1 | Utilities | Primary Solar Power System (Off-grid) | 85000
Phase 1 | Staff Housing | Murano Dome Staff Quarters (housing for 4–8) | 175000
Phase 2 | Greenhouse & Grotto | Central Greenhouse + Grotto Pool | 250000
Phase 2 | Aquafarming | Aquafarming Systems Setup | 120000
Phase 3 | Grand Opening | Final Preparations & Event Setup | 30000

## Funding Tracker
Source | Type | Amount Committed ($) | Received Date | Notes
Investor A | Equity | 150000 |  | Lead investor
Investor B | Equity | 100000 |  | Secondary investor
Commercial Loan | Loan | 800000 |  | 90% LTV
USDA Grant | Grant | 75000 |  | In application
Non-profit X | Grant | 50000 |  | Exploring eligibility

## Cashflow Timeline
Month | Planned Expenses ($) | Actual Expenses ($) | Planned Funding In ($) | Actual Funding In ($) | Cumulative Cash Balance ($)
Aug-2025 | 0 | 0 | 0 | 0 | 0
Sep-2025 | 0 | 0 | 0 | 0 | 0
Oct-2025 | 0 | 0 | 0 | 0 | 0
Nov-2025 | 0 | 0 | 0 | 0 | 0
Dec-2025 | 0 | 0 | 0 | 0 | 0
Jan-2026 | 0 | 0 | 0 | 0 | 0
Feb-2026 | 0 | 0 | 0 | 0 | 0
Mar-2026 | 0 | 0 | 0 | 0 | 0
Apr-2026 | 0 | 0 | 0 | 0 | 0
May-2026 | 0 | 0 | 0 | 0 | 0
Jun-2026 | 0 | 0 | 0 | 0 | 0
Jul-2026 | 0 | 0 | 0 | 0 | 0
Aug-2026 | 0 | 0 | 0 | 0 | 0
Sep-2026 | 0 | 0 | 0 | 0 | 0

## Staffing & Payroll
Role | Monthly Pay ($) | Start Month | End Month
Project Manager | 6000 | Aug-2025 | Sep-2026
Construction Crew | 20000 | Aug-2025 | Feb-2026
Electrician/Plumber | 7000 | Sep-2025 | Dec-2025
Chef/Kitchen Lead | 4000 | May-2026 | Sep-2026
Aquaculture Specialist | 5000 | Jan-2026 | Sep-2026

## Procurement Tracker
Item | Vendor | Qty | Estimated Cost ($) | Ordered | Received
Dome Kits | EcoDomes Inc. | 21 | 600000 | No
Solar Panels | SunPower | 50 | 85000 | No
Water Pumps | AgriFlow | 5 | 15000 | No
Greenhouse Glass | GreenGrow | 500 | 50000 | No
Fish Tanks | AquaSystems | 20 | 20000 | No

## Construction Timeline
Task | Start | End | Phase
Site Prep | Aug-2025 | Aug-2025 | Phase 1
Dome Cluster Installation | Sep-2025 | Dec-2025 | Phase 1
Murano Staff Dome Build | Aug-2025 | Oct-2025 | Phase 1
Utility Hookup | Oct-2025 | Dec-2025 | Phase 1
Solar Power System Installation | Oct-2025 | Nov-2025 | Phase 1
Greenhouse Build | Jan-2026 | Mar-2026 | Phase 2
Aquafarm Setup | Feb-2026 | Apr-2026 | Phase 2
Staff Onboarding | May-2026 | Jun-2026 | Phase 3
Soft Opening | Aug-2026 | Aug-2026 | Phase 3
Grand Opening | Sep-2026 | Sep-2026 | Phase 3